## Defects
name | defect_id | def_category | def_class | def_code | def_priority | def_status | CreatedOn | def_descr | def_note | def_unitOfMeasure | def_quantity | def_dateDue | def_dateCompleted | def_createdBy | def_completedBy | def_reason | def_condition | assetID | assetGroup | net_id | net_number | net_name | net_descr | net_locality | net_cway | net_roadSection | maintenance_class | fromPoRCh | por_type | fromPoRDescr | toPoRCh | toPoRDescr | Long | Lat | sysDateCreated | def_referral_to | def_referralDate | def_referral | Client_AssetStatus | Client_AssetType | Client_AssetID | Client_AssetName | Client_AssetHierarchy | pt_description | pt_quantity | pt_rate | pt_unitofmeasure | pt_cost
Network | 20.4148 | 2022 | LUMP_SUM | PGU01 | 28D | COMPLETED | 2022-10-25 08:09 | Penny lane West, mccrae | S/s to add rock and repair pot holes | LINM | 40 | 2022-11-22 08:09 | 2022-11-30 11:43 |  |  | NULL | PGU01.01 | 1938 | Network | 1938 | 302690 | PENNY LANE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | MCCRAE | S | 0302690__:0010:S | C | 16.871 | SE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 16.871 | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 144.9335 | -38.3464 | 2022-10-25 08:09 | NULL | NULL | NULL | NULL | Network | NULL | PENNY LANE | C | N/A | 0 | 0 | N/A | 0
Network | 1891.0569 | 2001 | LUMP_SUM | MEC01 | 1H | COMPLETED | 2022-11-21 16:30 | Penny Lane McCrae | M#2505684 Call out id 31685288 A/hrs attended location and SES and Shire were already onsite, nfa req | HRS | 1 | 2022-11-15 17:28 | 2022-11-21 16:30 |  |  | NULL | MEC01.01 | 1938 | Network | 1938 | 302690 | PENNY LANE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | MCCRAE | S | 0302690__:0010:S | C | 195.969 | SE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 195.969 | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 144.9344 | -38.3459 | 2022-11-21 16:30 | NULL | NULL | NULL | NULL | Network | NULL | PENNY LANE | C | N/A | 0 | 0 | N/A | 0
Network | 222655.0552 | 2022 | LUMP_SUM | PGU01 | 28D | COMPLETED | 2022-07-08 12:18 | Penny Lane West McCrae | Add rock to laneway when dryer. Large potholing occurring. M2464359 | LINM | 100 | 2022-08-05 12:17 | 2022-08-08 09:07 |  |  | NULL | PGU01.01 | 1938 | Network | 1938 | 302690 | PENNY LANE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | MCCRAE | S | 0302690__:0010:S | C | 11.641 | SE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 11.641 | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 144.9335 | -38.3464 | 2022-07-08 12:18 | NULL | NULL | NULL | NULL | Network | NULL | PENNY LANE | C | N/A | 0 | 0 | N/A | 0
Network | 585.0613 | 2010 | LUMP_SUM | PPR01 | 14D | COMPLETED | 2022-05-26 10:33 | View point Mc rae | please fill speed hump were meets the kerb | SQM | 5 | 2022-06-09 10:31 | 2022-06-09 11:35 |  |  | NULL | PPR01.03 | 6833 | Network | 6833 | 301042 | VIEW POINT ROAD | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | MCCRAE | S | 0301042__:0010:S | C | 107.336 | SE | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | 107.336 | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | 144.9349 | -38.3468 | 2022-05-26 10:33 | NULL | NULL | NULL | NULL | Network | NULL | VIEW POINT ROAD | C | N/A | 0 | 0 | N/A | 0
Network | 605.0613 | 2010 | LUMP_SUM | PPR01 | 14D | COMPLETED | 2022-06-10 06:59 | View point road Mc Crae | Were speed hump has been cut ,please add ash to fill up the gap /ring Neil | SQM | 2 | 2022-06-24 06:56 | 2022-06-28 09:25 |  |  | NULL | PPR01.03 | 6833 | Network | 6833 | 301042 | VIEW POINT ROAD | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | MCCRAE | S | 0301042__:0010:S | C | 110.655 | SE | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | 110.655 | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | 144.9348 | -38.3468 | 2022-06-10 06:59 | NULL | NULL | NULL | NULL | Network | NULL | VIEW POINT ROAD | C | N/A | 0 | 0 | N/A | 0
Network | 484.0571 | PPR | LUMP_SUM | RP01 | 14D | COMPLETED | 2021-01-06 14:17 | car park opp Penny lane Mccrae | car park opp Penny Lane ,drive in to car park the first parking spot on your right 1mt x2.5 were edge has broken away ,merit 2278556 | SQM | 4 | 2021-01-20 14:13 | 2021-01-15 09:08 |  |  | NULL | RP01.02 | 1938 | Network | 1938 | 302690 | PENNY LANE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | MCCRAE | S | 0302690__:0010:S | C | 192.1 | SE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 192.1 | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 144.9345 | -38.3459 | 2021-01-06 14:17 | NULL | NULL | NULL | NULL | Network | NULL | PENNY LANE | C | N/A | 0 | 0 | N/A | 0
Network | 851.4162 | 2028 | LUMP_SUM | RLC01 | 3D | COMPLETED | 2021-08-06 08:56 | mccrae Foreshore | M#2351253 Under investigation | SQM | 0.1 | 2021-08-09 08:56 | 2021-08-06 09:02 |  |  | NULL | RLC01.01 | 1938 | Network | 1938 | 302690 | PENNY LANE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | MCCRAE | S | 0302690__:0010:S | C | 180.216 | SE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 180.216 | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 144.9345 | -38.346 | 2021-08-06 08:56 | NULL | NULL | NULL | NULL | Network | NULL | PENNY LANE | C | N/A | 0 | 0 | N/A | 0
Network | 867.4162 | 2028 | LUMP_SUM | RLC01 | 7D | COMPLETED | 2021-08-09 07:34 | Bay Track opp 605 Pt Nepean Rd, McCrae | M#2351165 approx 1mtr | SQM | 1 | 2021-08-16 07:34 | 2021-08-09 07:43 |  |  | NULL | RLC01.02 | 1938 | Network | 1938 | 302690 | PENNY LANE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | MCCRAE | S | 0302690__:0010:S | C | 176.879 | SE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 176.879 | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 144.9345 | -38.3461 | 2021-08-09 07:34 | NULL | NULL | NULL | NULL | Network | NULL | PENNY LANE | C | N/A | 0 | 0 | N/A | 0
Network | 6745.0593 | 2022 | LUMP_SUM | PGU01 | 28D | COMPLETED | 2021-08-16 09:25 | On Penny Lane west 20m in from Pt Nepean Rd | Bobcat gravel patching required to fill potholes . 3 or 4 buckets required . | LINM | 50 | 2021-09-13 09:18 | 2021-08-20 10:23 |  |  | NULL | PGU01.01 | 1938 | Network | 1938 | 302690 | PENNY LANE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | MCCRAE | S | 0302690__:0010:S | C | 15.711 | SE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 15.711 | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 144.9335 | -38.3464 | 2021-08-16 09:25 | NULL | NULL | NULL | NULL | Network | NULL | PENNY LANE | C | N/A | 0 | 0 | N/A | 0
Network | 215334.0545 | UPAVT | LUMP_SUM | UR05 | 28D | COMPLETED | 2020-06-02 09:50 | Penny Lane, West | M# 2203318 Gravel patch potholes as needed - allow little topper load of rock | SQM | 80 | 2020-06-30 09:47 | 2020-06-10 08:40 |  |  | NULL | UR05.01 | 1938 | Network | 1938 | 302690 | PENNY LANE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | MCCRAE | S | 0302690__:0010:S | C | 31.6 | SE | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 31.6 | PENNY LANE-[E] POINT NEPEAN RD to DEAD END | 144.9336 | -38.3466 | 2020-06-02 09:50 | NULL | NULL | 0 | NULL | Network | NULL | PENNY LANE | C | N/A | 0 | 0 | N/A | 0
Network | 651.0571 | 2010 | LUMP_SUM | PPR01 | 14D | COMPLETED | 2021-04-14 14:24 | Prospect Hill Rd, Mccrae | Repair pothole O/S #1 merit #2317841 | SQM | 1 | 2021-04-28 14:21 | 2021-04-19 14:00 |  |  | NULL | PPR01.03 | 4301 | Network | 4301 | 301444 | PROSPECT HILL ROAD | PROSPECT HILL ROAD-[S] VIEW POINT RD to THE EYRIE | MCCRAE | S | 0301444__:0020:S | C | 191.8 | SE | PROSPECT HILL ROAD-[S] VIEW POINT RD to THE EYRIE | 191.8 | PROSPECT HILL ROAD-[S] VIEW POINT RD to THE EYRIE | 144.9376 | -38.3468 | 2021-04-14 14:24 | NULL | NULL | NULL | NULL | Network | NULL | PROSPECT HILL ROAD | C | N/A | 0 | 0 | N/A | 0
Network | 2030.0593 | PPR | LUMP_SUM | RP01 | 14D | COMPLETED | 2020-02-20 09:36 | 1 x pothole , beside kerb , o/s # 14 Prospect Hill rd . |  | SQM | 0.8 | 2020-03-05 09:34 | 2020-03-04 13:54 |  |  | NULL | RP01.02 | 4301 | Network | 4301 | 301444 | PROSPECT HILL ROAD | PROSPECT HILL ROAD-[S] VIEW POINT RD to THE EYRIE | MCCRAE | S | 0301444__:0020:S | C | 61.1 | SE | PROSPECT HILL ROAD-[S] VIEW POINT RD to THE EYRIE | 61.1 | PROSPECT HILL ROAD-[S] VIEW POINT RD to THE EYRIE | 144.9364 | -38.3463 | 2020-02-20 09:36 | NULL | NULL | 0 | NULL | Network | NULL | PROSPECT HILL ROAD | C | N/A | 0 | 0 | N/A | 0
Network | 42.0591 | LDRAIN | PW | LD04 | 5Y | COMPLETED | 2019-11-21 07:34 | 4 Margaret St McCrae | Repair to the 600mm pipeline & create bund wall to protect property | ITEM | 4.8 | 2024-06-06 07:32 | 2019-07-03 12:00 |  |  | NULL | NA | 4795 | Network | 4795 | 301368 | MARGARET STREET | MARGARET STREET-[E] POINT NEPEAN RD to DEAD END | MCCRAE | S | 0301368__:0010:S | C | 90.8 | SE | MARGARET STREET-[E] POINT NEPEAN RD to DEAD END | 90.8 | MARGARET STREET-[E] POINT NEPEAN RD to DEAD END | 144.9333 | -38.3472 | 2019-11-21 07:34 | NULL | NULL | 0 | NULL | Network | NULL | MARGARET STREET | C | N/A | 0 | 0 | N/A | 0
Network | 736.0612 | 2022 | LUMP_SUM | PGU01 | 28D | COMPLETED | 2022-11-08 14:04 | whole Road | M# 2498431 smooth over the roadway and go right up to the concrete driveway at the end to the left as this is a part of the road reserve, path to View Point Road | LINM | 50 | 2022-12-06 14:00 | 2022-12-07 09:18 |  |  | NULL | PGU01.01 | 4795 | Network | 4795 | 301368 | MARGARET STREET | MARGARET STREET-[E] POINT NEPEAN RD to DEAD END | MCCRAE | S | 0301368__:0010:S | C | 83.434 | SE | MARGARET STREET-[E] POINT NEPEAN RD to DEAD END | 83.434 | MARGARET STREET-[E] POINT NEPEAN RD to DEAD END | 144.9332 | -38.3471 | 2022-11-08 14:04 | NULL | NULL | NULL | NULL | Network | NULL | MARGARET STREET | C | N/A | 0 | 0 | N/A | 0
Network | 215597.0545 | UPAVT | LUMP_SUM | UR02 | 28D | COMPLETED | 2020-11-19 15:10 | from where you finished last week to the concrete drive of number 8 | M# 2257021 Brush over to the concrete driveway of number 8, as Margret St actually swings around past number 8's driveway and turns into a walking track. | SQM | 50 | 2020-12-17 15:05 | 2020-11-24 |  |  | NULL | UR02.01 | 4795 | Network | 4795 | 301368 | MARGARET STREET | MARGARET STREET-[E] POINT NEPEAN RD to DEAD END | MCCRAE | S | 0301368__:0010:S | C | 94.8 | SE | MARGARET STREET-[E] POINT NEPEAN RD to DEAD END | 94.8 | MARGARET STREET-[E] POINT NEPEAN RD to DEAD END | 144.9333 | -38.3472 | 2020-11-19 15:10 | NULL | NULL | NULL | NULL | Network | NULL | MARGARET STREET | C | N/A | 0 | 0 | N/A | 0
Network | 246.0591 | BWALK | PW | BW05 | 5Y | COMPLETED | 2020-03-31 09:10 | The Eyrie McCrae - Stairs | Remove the rotted and failing timber edge strips to the concrete steps & replace with new timbers | ITEM | 8 | 2025-01-27 09:08 | 2020-03-03 12:00 |  |  | NULL | NA | 6320 | Network | 6320 | 301209 | THE EYRIE | THE EYRIE-[S] WONGA GV to PROSPECT HILL RD | MCCRAE | S | 0301209__:0010:S | C | 42.2 | SE | THE EYRIE-[S] WONGA GV to PROSPECT HILL RD | 42.2 | THE EYRIE-[S] WONGA GV to PROSPECT HILL RD | 144.9387 | -38.3451 | 2020-03-31 09:10 | NULL | NULL | 0 | NULL | Network | NULL | THE EYRIE | C | N/A | 0 | 0 | N/A | 0
Network | 1757.0569 | 2001 | LUMP_SUM | MEC01 | 1H | COMPLETED | 2022-09-20 10:11 | NULL | NULL | HRS | 1 | 2022-09-20 11:11 | 2022-09-14 10:09 |  |  | NULL | MEC01.01 | 6320 | Network | 6320 | 301209 | THE EYRIE | THE EYRIE-[S] WONGA GV to PROSPECT HILL RD | MCCRAE | S | 0301209__:0010:S | C | 286.583 | SE | THE EYRIE-[S] WONGA GV to PROSPECT HILL RD | 286.583 | THE EYRIE-[S] WONGA GV to PROSPECT HILL RD | 144.9377 | -38.3466 | 2022-09-20 10:11 | NULL | NULL | NULL | NULL | Network | NULL | THE EYRIE | C | N/A | 0 | 0 | N/A | 0
Network | 2029.0593 | NKR | LS | KC02 | 60D | TASKED | 2020-02-20 09:30 | Replace 2m f damaged kerb & channel on cnr of Wonga gv & The Eyrie . |  | LINM | 2 | 2020-04-20 09:28 | NULL |  |  | NULL | KC02.01 | 6320 | Network | 6320 | 301209 | THE EYRIE | THE EYRIE-[S] WONGA GV to PROSPECT HILL RD | MCCRAE | S | 0301209__:0010:S | C | 35.2 | SE | THE EYRIE-[S] WONGA GV to PROSPECT HILL RD | 35.2 | THE EYRIE-[S] WONGA GV to PROSPECT HILL RD | 144.9388 | -38.3451 | 2020-02-20 09:30 | NULL | NULL | 0 | NULL | Network | NULL | THE EYRIE | C | N/A | 0 | 0 | N/A | 0
Network | 393.06 | 2001 | LUMP_SUM | MEC01 | 1H | COMPLETED | 2021-08-02 09:28 | 5 View Point Road MCCRAE | After Hours Callout ID: 28321541 GR attended, assessed site and phoned through to Parks to attend M# 2351120 | HRS | 1 | 2021-08-31 10:25 | 2021-07-31 09:28 |  |  | NULL | MEC01.01 | 6833 | Network | 6833 | 301042 | VIEW POINT ROAD | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | MCCRAE | S | 0301042__:0010:S | C | 60.337 | SE | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | 60.337 | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | 144.9354 | -38.3468 | 2021-08-02 09:28 | NULL | NULL | NULL | NULL | Network | NULL | VIEW POINT ROAD | C | N/A | 0 | 0 | N/A | 0
Network | 2031.0593 | NKR | PM | KC02 | 10Y | TASKED | 2020-02-20 09:45 | Replace damaged K&C o/s # 16 View Point rd . |  | LINM | 14 | 2030-02-20 09:43 | NULL |  |  | NULL | KC02.02 | 6833 | Network | 6833 | 301042 | VIEW POINT ROAD | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | MCCRAE | S | 0301042__:0010:S | C | 135.9 | SE | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | 135.9 | VIEW POINT ROAD-[S] PROSPECT HILL RD to DEAD END | 144.9345 | -38.3469 | 2020-02-20 09:45 | NULL | NULL | 0 | NULL | Network | NULL | VIEW POINT ROAD | C | N/A | 0 | 0 | N/A | 0