## Link to Spatial Data
Open link | https://www.google.com/maps/d/edit?mid=1syjWRzRR6sIsRSdcIZTvxtJj7jcqSPRF&ll=-38.3260367540701%2C144.9628165669542&z=14
NOTE - The link is VIEW only. If you want to edit rights to the map, you will need to sign into Asset Management's Google Account.
To get map on mobile phone for driving directions | Demonstrated in YouTube video
https://www.youtube.com/watch?v=gLAvI1mg38k
Sign into AM account on mobile phone
Open google maps in phone
Click the three horizontal bars next to google map bar and select Your Places
Go to Maps and select the map to display
Asset Management Google Account - Please tell Asset Management prior if you need edit rights
Username: | I&S | I&S | I&S
Password: | I&S | I&S | I&S

## Link to Photos
Objective Ref: | A9039278
Photos taken during site visits in August 2019
Photos grouped by works type - Renewal or Maintenance as listed in the spatial data

## Kerb Projected 5-year CWProgram
Layer Name in Spatial Google Maps | Road Name | Township | On Reseal Program | Survey Date | Description | Length (m) | Cost Estimate (Proposed Actual) | Cost Estimate (include 9% cont to match Downer) | Priority | Look into Reseal? | Comments with Brandon 3/8/19 |  | Quantity | Estimate (Proposed Actual) | Estimate (inc. 9% cont to match Downer) | Past Info |  | LTFP | Project budget | Standard kerb reseal budget | Proposed total budget
2020-21 Kerb reseal budget | Donald St | ROSEBUD | 2020/21 | 2019-08-08 | Renew left kerb from Hope St to Maysbury Ave with reseal | 60 | 24000 | 26160 | 2 | Yes | Exclude, isolated sections expend from standard 20-21 kerb reseal budget | 2020-21 Kerb reseal budget | 5 | 527600 | 575084 | For 2019/20 - Budget was $1,139,000 of which $262,386 is for additional kerbs (reseals and merits) |  | 2020-21 | 1239200 | 250000 | 1489200
2020-21 Kerb reseal budget | Murrowong Ave | ROSEBUD | 2020/21 | 2019-08-08 | Renew sections both kerbs as required with reseal | 400 | 160000 | 174400 | 2 | Yes | Allocate to 20-21 kerb reseal budget. Brandon to discuss with Downer to increase reseal extent to include section between The Drive and Coorabong Avenue. | 2020-21 Renewal | 4 | 711600 | 775644 | For 2020/21 - |  | 2021-22 | 1304800 | 250000 | 1554800
2020-21 Kerb reseal budget | GRACE STREET | RYE | 2020/21 | 2019-08-05 | Renew left kerb from Weir St to Lyons St with reseal | 269 | 107600 | 117284 | 2 |  | Allocate to 20-21 kerb reseal budget | 2021-22 Renewal | 9 | 1304800 | 1422232 | 4 Project bids | 711600 | 2022-23 | 1307333.3333 | 250000 | 1557333.3333
2020-21 Kerb reseal budget | Melbourne Rd | Sorrento | 2020/21 | 2019-08-29 | Renew sections both kerbs as required with reseal around roundabout | 120 | 48000 | 52320 | 3 | Yes | Exclude, isolated sections expend from standard 20-21 kerb reseal budget | Future Renewal Priority 3,4,5 | 25 | 3922000 | 4274980 | 3 Kerb reseal projects | 527600 | 2023-24 | 1307333.3333 | 250000 | 1557333.3333
[12 empty] | Future Renewal Priority 6,7,8 | 25 | 2398400 | 2614256 | Standard kerb reseal budget | 250000 | 2024-25 | 1307333.3333 | 250000 | 1557333.3333
2020-21 Renewal | View Point Road | McCrae | #N/A | 2019-08-12 | Renew both kerbs in court & adjoining section along Prospect Hill Rd | 352 | 140800 | 153472 | 1 |  | Project bid | Future Renewal Priority 8,9,10 | 31 | 3666000 | 3995940 | Total | 1489200 | 2025-26 | 1347644.4444 | 250000 | 1597644.4444
2020-21 Renewal | Park Ave | Capel Sound | #N/A | 2019-08-13 | Renew both kerbs from Nepean Hwy to Eastbourne Rd | 647 | 258800 | 282092 | 1 |  | Project bid | [6 empty] | 2026-27 | 1347644.4444 | 250000 | 1597644.4444
2020-21 Renewal | Wellington St | Mornington | #N/A | 2019-08-23 | Renew both kerbs from Barkly St to Cromwell St | 600 | 240000 | 261600 | 1 |  | Project bid | [6 empty] | 2027-28 | 1347644.4444 | 250000 | 1597644.4444
2020-21 Renewal | Woodland Ave | Mount Eliza | #N/A | 2019-08-27 | Renew entire kerb in court | 180 | 72000 | 78480 | 1 |  | Project bid | [6 empty] | 2028-29 | 1347644.4444 | 250000 | 1597644.4444
2020-21 Kerb reseal budget | Gipps St & Foam St | ROSEBUD | #N/A | 2019-08-07 | Put on reseal list. Renew both kerbs on Gipps & Foam Street with reseal. | 650 | 260000 | 283400 | 1 | Yes | Re-prioritised from 2 to 1. Allocate to 20-21 kerb reseal budget. Brandon to discuss with Downer to include in 20-21 reseal list. | [6 empty] | 2029-30 | 1347644.4444 | 250000 | 1597644.4444
2021-22 Renewal | Seventh Ave | ROSEBUD | #N/A | 2019-08-08 | Renew both kerbs from Mt Arthur Rd to Head St | 828 | 331200 | 361008 | 1
2021-22 Renewal | Ocean Beach Rd | Sorrento | #N/A | 2019-08-29 | Renew right kerb from motel to carpark entry | 262 | 104800 | 114232 | 2
2021-22 Renewal | Wonga Grove | McCrae | #N/A | 2019-08-12 | Renew both kerbs from Howitt St to Coburn Ave | 267 | 106800 | 116412 | 2 |  | Re-priortised from 1 to 2
2021-22 Renewal | Prospect Hill Road | McCrae | #N/A | 2019-08-12 | Renew right kerb from #7 to Coburn Ave + Renew left kerb from #8 to Coburn Ave (potentially delay until development at #9 complete) | 173 | 69200 | 75428 | 2
2021-22 Renewal | Barry St | ROSEBUD | #N/A | 2019-08-07 | Renew both kerbs from Spray St to Rosebud Pde | 163 | 65200 | 71068 | 2
2021-22 Renewal | Rosebud Pde | ROSEBUD | #N/A | 2019-08-07 | Renew left kerb from Gipps St to Barry St | 79 | 31600 | 34444 | 2
2021-22 Renewal | Keogh St | ROSEBUD | #N/A | 2019-08-12 | Renew both kerbs from Jetty Rd to Leon Ave (worst section btw Jetty & Potton Ave) | 666 | 266400 | 290376 | 2
2021-22 Renewal | Macedon Ave | Dromana | #N/A | 2019-08-14 | Renew left kerb from Jetty Rd to approx. #12 + Renew right kerb from Jetty Rd to Frieda St | 434 | 173600 | 189224 | 2 |  | Re-prioritised from 3 to 2
2021-22 Renewal | Canadian Bay Rd | Mount Eliza | #N/A | 2019-08-27 | Renew right kerb from Camborne Ave south adjacent to SEP outside community hall | 390 | 156000 | 170040 | 2
Maintenance - High priority | Newton Ave | Sorrento |  |  | Refer to photo in spatial Google Maps | [5 empty] | Brandon to revisit when signing off Coppin Rd Capital Works hand over
Maintenance - High priority | Ocean Beach Rd | Sorrento |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Beth Court | ROSEBUD |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Dunsmuir Dr | ROSEBUD |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Deighton Dr | ROSEBUD |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Beatty Pde | ROSEBUD |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Foam St | ROSEBUD |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Rosemore Rd | ROSEBUD |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Butler Ave | Mornington |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Maxwell St | Mornington |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Venice St | Mornington |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Adelaide St | Mornington |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Old Mornington Rd | Mount Eliza |  |  | Refer to photo in spatial Google Maps
Maintenance - High priority | Walter St | Safety Beach |  |  | Refer to photo in spatial Google Maps
To be deleted | Hillside Ave | Dromana | #N/A | 2019-08-14 | Both kerbs from Boundary Rd to Burns Cl | 650 | 260000 | 283400 | 2 | Yes | To be removed - on 2019/20 list for road and kerb works
To be deleted | King St | Flinders | 2019/20 | 2019-08-19 | Kerbs to be considered as part of road reconstruction | 780 | 312000 | 340080 | 3 | Yes | To be removed - on 2019/20 list for road and kerb works
Future Renewal Priority 3,4,5 | Third Ave | ROSEBUD | #N/A | 2019-08-08 | Renew both kerbs from Mt Arthur Rd to Nepean Hwy | 810 | 324000 | 353160 | 2
Future Renewal Priority 3,4,5 | Heales St | Dromana | #N/A | 2019-08-13 | Both kerbs from Nepean Hwy to Ligar St (note maybe major development opposite 7-Eleven) | 950 | 380000 | 414200 | 3 | Yes | Re-priortised from 2 to 3
Future Renewal Priority 3,4,5 | Verdon St | Dromana | #N/A | 2019-08-13 | Both kerbs from Ligar St to end of court (include section on Ligar St moderate ponding issues particularly outside 19) | 496 | 198400 | 216256 | 3 | Yes
Future Renewal Priority 3,4,5 | Verdon St | Dromana | #N/A | 2019-08-13 | Left kerb from Ligar St to Hodgkinson St + Renew sections along right kerb and Ligar St as required | 470 | 188000 | 204920 | 3 | Yes
Future Renewal Priority 3,4,5 | Verdon St | Dromana | #N/A | 2019-08-13 | Right kerb from Nepean Hwy to No. 2 Verdon St | 162 | 64800 | 70632 | 3
Future Renewal Priority 3,4,5 | Latrobe Parade | Dromana | #N/A | 2019-08-13 | Left kerb from McArthur St to Foote St | 120 | 48000 | 52320 | 3
Future Renewal Priority 3,4,5 | Frieda St | Dromana | #N/A | 2019-08-14 | Left kerb from Palmerston Ave to Dyson St + Right kerb from Macedon Ave to You Yangs Ave | 394 | 157600 | 171784 | 3
Future Renewal Priority 3,4,5 | MacDonalds Grove | Mornington | #N/A | 2019-08-26 | Renew sections both sides as required | 600 | 240000 | 261600 | 3
Future Renewal Priority 3,4,5 | Hampden St | Mornington | #N/A | 2019-08-23 | Left kerb from Wilsons Rd to Main St | 588 | 235200 | 256368 | 3
Future Renewal Priority 3,4,5 | Tanti Ave (Barkly St end) | Mornington | #N/A | 2019-08-26 | Left kerb from Barkly St to bus stop outside 107 | 392 | 156800 | 170912 | 3 |  | Re-priortised from 2 to 3
Future Renewal Priority 3,4,5 | Tanti Ave (Barkly St end) | Mornington | #N/A | 2019-08-26 | Right kerb from Barkly St to 88 | 328 | 131200 | 143008 | 3 |  | Re-priortised from 2 to 3
Future Renewal Priority 3,4,5 | First Ave | ROSEBUD | #N/A | 2019-08-08 | Both kerbs from Mt Arthur Rd to House no. 27 | 284 | 113600 | 123824 | 3 |  | Re-priortised from 2 to 3, possible broken main reported
Future Renewal Priority 3,4,5 | Murray-Anderson Rd | ROSEBUD | #N/A | 2019-09-03 | Both kerbs from Mitchell St to Cass St | 760 | 304000 | 331360 | 3 |  | Re-priortised from 2 to 3
Future Renewal Priority 3,4,5 | Thomas St | ROSEBUD | #N/A | 2019-08-08 | Renew sections as required | 235 | 94000 | 102460 | 3
Future Renewal Priority 3,4,5 | Windella Ave | ROSEBUD | #N/A | 2019-08-08 | Renew sections as required both sides | 264 | 105600 | 115104 | 3
Future Renewal Priority 3,4,5 | Warraburra Ave | ROSEBUD | #N/A | 2019-08-08 | Renew sections as required both sides | 269 | 107600 | 117284 | 3
Future Renewal Priority 3,4,5 | Sixth Ave | ROSEBUD | #N/A | 2019-08-08 | Both kerbs from Mt Arthur Rd to Nepean Hwy | 1012 | 404800 | 441232 | 3
Future Renewal Priority 3,4,5 | Mark St | ROSEBUD | #N/A | 2019-08-12 | Both kerbs from Jetty Rd to Murray-Anderson Rd (wait till development at #27 finishes) | 370 | 148000 | 161320 | 3
Future Renewal Priority 3,4,5 | Frankston-Flinders Service Rd between Reid Pde & Autumn Ct | Hastings | #N/A | 2019-08-20 | Renew sections of kerb both sides as required. | 250 | 100000 | 109000 | 3
Future Renewal Priority 3,4,5 | Frankston-Flinders Service Rd north of Haddock St | Hastings | #N/A | 2019-08-20 | Renew sections of kerb both sides as required. | 250 | 100000 | 109000 | 3
Future Renewal Priority 3,4,5 | High Street | Hastings | #N/A | 2019-08-20 | Renew section between railway tracks and Supercheap Auto | 100 | 40000 | 43600 | 3
Future Renewal Priority 3,4,5 | Beach Grove | Mornington | #N/A | 2019-08-23 | Renew both kerbs | 340 | 136000 | 148240 | 3 | Yes
Future Renewal Priority 3,4,5 | Spray St | Mornington | #N/A | 2019-08-26 | Renew section outside petrol station | 50 | 20000 | 21800 | 3
Future Renewal Priority 3,4,5 | Tallis Drive | Mornington | #N/A | 2019-08-26 | Either patch repair uplifted kerb from large trees as reported or renew entire kerb length. Will damage again due to tree specie. | 216 | 86400 | 94176 | 3
Future Renewal Priority 3,4,5 | Jacksons Rd | Mount Eliza | #N/A | 2019-08-27 | Patch repairs as reported or renew - displacement will be ongoing due to large trees | 95 | 38000 | 41420 | 3
Future Renewal Priority 6,7,8 | Rye launching ramp car park access | RYE | 2020/21 | 2019-08-06 |  | 58 | 23200 | 25288 | 4 |  | Uncertain - Pending Rye Foreshore Masterplan
Future Renewal Priority 6,7,8 | Melbourne Rd Service Rd | RYE | #N/A | 2019-08-06 |  | 72 | 28800 | 31392 | 4
Future Renewal Priority 6,7,8 | Lawson Crescent | ROSEBUD | #N/A | 2019-08-12 | Kerb on even house number side from Jetty Rd to Murray-Anderson Rd | 233 | 93200 | 101588 | 4 | Yes
Future Renewal Priority 6,7,8 | Coburn Ave | McCrae | #N/A | 2019-08-12 | Left kerb from Burrell St to Prospect Hill Rd (potentially delay until development done) | 317 | 126800 | 138212 | 4
Future Renewal Priority 6,7,8 | Coburn Ave | McCrae | #N/A | 2019-08-12 | From Point Nepean Rd to Burrell St | 114 | 45600 | 49704 | 4 | Yes
Future Renewal Priority 6,7,8 | Thomas St | Dromana | #N/A | 2019-08-14 | Both kerbs from McCulloch St to Francis St - delay till developments done | 213 | 85200 | 92868 | 4 | Yes
Future Renewal Priority 6,7,8 | Pier St | Dromana | #N/A | 2019-08-14 | Left kerb from Charles St to NTR end | 245 | 98000 | 106820 | 4 | Yes
Future Renewal Priority 6,7,8 | Elizabeth Ave | Dromana | #N/A | 2019-08-14 | Both kerbs renew sections as required between Frieda St and Mary St | 480 | 192000 | 209280 | 4
Future Renewal Priority 6,7,8 | Panoramic Ave | Dromana | #N/A | 2019-08-14 | Left kerb from Jetty Rd to Mary St + Right kerb from Jetty Rd to approx. #316 | 464 | 185600 | 202304 | 4
Future Renewal Priority 6,7,8 | Dromana Pde | Dromana | #N/A | 2019-08-15 | Both kerb Renew sections as required from Balmoral Ave to Clyde Rd | 150 | 60000 | 65400 | 4
Future Renewal Priority 6,7,8 | Bruce Rd | Mount Martha | #N/A | 2019-08-15 |  | 90 | 36000 | 39240 | 4
Future Renewal Priority 6,7,8 | Kilburn Grove | Mount Martha | #N/A | 2019-08-15 | Both kerbs from approx. no.70 to Ferrero Grove | 554 | 221600 | 241544 | 4
Future Renewal Priority 6,7,8 | Mornington-Tyabb Rd Service Rd, Mornington | Mornington | #N/A | 2019-08-16 | Roll over kerb from Progress St to Bruce St | 105 | 42000 | 45780 | 4
Future Renewal Priority 6,7,8 | Mornington-Tyabb Rd Service Rd, Mornington | Mornington | #N/A | 2019-08-16 | Rollover kerb east of Milgate Dr | 69 | 27600 | 30084 | 4
Future Renewal Priority 6,7,8 | Roundabout kerb Bentons Rd-Racecourse Rd, Mornington | Mornington | #N/A | 2019-08-16 | Renew kerb around roundabout | 40 | 16000 | 17440 | 4
Future Renewal Priority 6,7,8 | The Esplanade | Flinders | #N/A | 2019-08-19 | Replace sections of kerb both sides as required particularly at slow point and intersection of Hurst St. | 200 | 80000 | 87200 | 4 | Yes
Future Renewal Priority 6,7,8 | The Esplanade | Flinders | #N/A | 2019-08-19 | Replace sections of kerb both sides as required particularly at slow point and intersection of Gordon St | 200 | 80000 | 87200 | 4 | Yes
Future Renewal Priority 6,7,8 | Jordan St | Somerville | #N/A | 2019-08-22 | Renew sections of left kerb from Majestic Dr to Eramosa Rd E as required | 232 | 92800 | 101152 | 4
Future Renewal Priority 6,7,8 | Guelph St | Somerville | #N/A | 2019-08-22 | Renew sections both sides as required - industrial area. | 200 | 80000 | 87200 | 4 | Yes
Future Renewal Priority 6,7,8 | Raymond St | Somerville | #N/A | 2019-08-22 | Renew sections both sides as required | 200 | 80000 | 87200 | 4
Future Renewal Priority 6,7,8 | Roundabout kerb Osborne Dr-Helena St, Mount Martha | Mount Martha | #N/A | 2019-08-23 | Renew kerb at roundabout | 45 | 18000 | 19620 | 4
Future Renewal Priority 6,7,8 | Swansea Grove | Mornington | #N/A | 2019-08-23 | Renew both kerbs | 565 | 226000 | 246340 | 4 | Yes
Future Renewal Priority 6,7,8 | Tanti Ave (Nepean Hwy end) | Mornington | #N/A | 2019-08-26 | Check in future allowed both kerbs from bus stop outside 107 to Nepean Hwy end | 917 | 366800 | 399812 | 4
Future Renewal Priority 6,7,8 | Watts Parade | Mount Eliza | #N/A | 2019-08-27 | Left kerb from Williams Rd to #19 | 93 | 37200 | 40548 | 4
Future Renewal Priority 6,7,8 | Kunyung Rd | Mount Eliza | #N/A | 2019-08-27 | Monitor for future renewal - sunk kerb outside #5, development at #9,11. | 140 | 56000 | 61040 | 4
Future Renewal Priority 8,9,10 | Hooper Grove | Mount Martha | 2019/20 | 2019-08-15 | Consider future years roll over kerb type | 200 | 80000 | 87200 | 5
Future Renewal Priority 8,9,10 | Shelbourne Court | Mornington | 2019/20 | 2019-08-26 | Renew sections as required | 200 | 80000 | 87200 | 5
Future Renewal Priority 8,9,10 | Rosebud Pde | ROSEBUD | #N/A | 2019-08-07 | Both kerbs from McDowell St to Wannaeue Pl | 155 | 62000 | 67580 | 5
Future Renewal Priority 8,9,10 | Rosebud Pde | ROSEBUD | #N/A | 2019-08-07 | Left kerb from Gipps St to McDowell St - schedule after development | 141 | 56400 | 61476 | 5
Future Renewal Priority 8,9,10 | Maysbury Ave | ROSEBUD | #N/A | 2019-08-08 | Renew sections as required both sides | 177 | 70800 | 77172 | 5 | Yes
Future Renewal Priority 8,9,10 | McCombe St | ROSEBUD | #N/A | 2019-08-08 | Left kerb from Ross Ave to Thomas St | 101 | 40400 | 44036 | 5
Future Renewal Priority 8,9,10 | McCombe St | ROSEBUD | #N/A | 2019-08-08 | Right kerb from Ross Ave to First Ave | 231 | 92400 | 100716 | 5
Future Renewal Priority 8,9,10 | Mark St | ROSEBUD | #N/A | 2019-08-12 | Check in future - both kerbs east of Murray-Anderson Rd to approx. Hampton Ct | 315 | 126000 | 137340 | 5
Future Renewal Priority 8,9,10 | The Avenue | McCrae | #N/A | 2019-08-12 | Left kerb from Point Nepean Rd to Hiilary Ave | 565 | 226000 | 246340 | 5 | Yes
Future Renewal Priority 8,9,10 | Rae St | Capel Sound | #N/A | 2019-08-13 | Both kerbs from Ella Crescent to approx. house no. 7 | 107 | 42800 | 46652 | 5
Future Renewal Priority 8,9,10 | Timara Court | McCrae | #N/A | 2019-08-13 | All kerbs around court (note potential development happening) | 143 | 57200 | 62348 | 5
Future Renewal Priority 8,9,10 | Farey Ave | Dromana | #N/A | 2019-08-13 | Both kerbs from Latrobe Pde to Clarendon St | 400 | 160000 | 174400 | 5 | Yes
Future Renewal Priority 8,9,10 | Clarendon St | Dromana | #N/A | 2019-08-13 | Both kerbs from approx. house no. 71 to no through road end | 221 | 88400 | 96356 | 5
Future Renewal Priority 8,9,10 | Davey Ave | Dromana | #N/A | 2019-08-14 | Both kerbs renew sections as required between Palmerston Ave & Mary St | 388 | 155200 | 169168 | 5
Future Renewal Priority 8,9,10 | Overbay Ave | Dromana | #N/A | 2019-08-14 | Both kerbs from Kent St to Somerset Dr | 255 | 102000 | 111180 | 5
Future Renewal Priority 8,9,10 | Lansell Ave | Safety Beach | #N/A | 2019-08-15 | Both kerbs from Pickings Rd to Coveside Ave | 200 | 80000 | 87200 | 5
Future Renewal Priority 8,9,10 | Coveside Ave | Safety Beach | #N/A | 2019-08-15 | Left kerb from 53 to Lansell Ave | 155 | 62000 | 67580 | 5
Future Renewal Priority 8,9,10 | Mount Martha Rd | Mount Martha | #N/A | 2019-08-15 | Right kerb from Ellerina Rd to Grandview Tce - consider future years | 245 | 98000 | 106820 | 5
Future Renewal Priority 8,9,10 | Service Rd south west of Flinders Park-Mornington Tyabb Rd | Mornington | #N/A | 2019-08-16 | Renew entry kerbs and median | 60 | 24000 | 26160 | 5 | Yes
Future Renewal Priority 8,9,10 | Winona Rd | Mount Eliza | #N/A | 2019-08-16 | Renew sections as required | 1000 | 400000 | 436000 | 5
Future Renewal Priority 8,9,10 | Allison Rd | Mount Eliza | #N/A | 2019-08-16 | Renew sections as required | 1000 | 400000 | 436000 | 5
Future Renewal Priority 8,9,10 | Woolleys Rd | Bittern | #N/A | 2019-08-20 | Reinspect in future years if need renewing | 300 | 120000 | 130800 | 5
Future Renewal Priority 8,9,10 | Wingala Court | Hastings | #N/A | 2019-08-20 | Renew kerb in court | 183 | 73200 | 79788 | 5
Future Renewal Priority 8,9,10 | Pynble Court | Hastings | #N/A | 2019-08-20 | Renew kerb in court | 133 | 53200 | 57988 | 5
Future Renewal Priority 8,9,10 | Stanley St | Somerville | #N/A | 2019-08-22 | Future check - Renew both sides between Eramosa Rd E and Sullivan Dr | 140 | 56000 | 61040 | 5
Future Renewal Priority 8,9,10 | Prince St | Mornington | #N/A | 2019-08-23 | Renew sections as required | 163 | 65200 | 71068 | 5
Future Renewal Priority 8,9,10 | Kent St | Mornington | #N/A | 2019-08-23 | Renew both kerbs | 464 | 185600 | 202304 | 5
Future Renewal Priority 8,9,10 | Queen St | Mornington | #N/A | 2019-08-23 | Aged kerb consider renew both sides | 153 | 61200 | 66708 | 5
Future Renewal Priority 8,9,10 | Beatty Pde | Mornington | #N/A | 2019-08-26 | Consider overall condition in future - for mean time repair significantly displaced kerbing outside 10 and 12 Beatty Pde as part of maintenance | 600 | 240000 | 261600 | 5
Future Renewal Priority 8,9,10 | Williams Rd | Mount Eliza | #N/A | 2019-08-27 | Check for future renewal semi mount sit on kerb type between Watts Pde and foreshore | 170 | 68000 | 74120 | 5
Future Renewal Priority 8,9,10 | Watts Parade | Mount Eliza | #N/A | 2019-08-27 | Right kerb - Check for future renewal aged kerb from ongoing water flow, irrigation from Daveys Bay Rd to Williams Rd | 600 | 240000 | 261600 | 5
Future Stone Kerbs - Mornington Area | View St | Mornington | #N/A | 2019-08-23 | Stone kerbing both sides - For Service Delivery to consider renewal plan i.e. maintain character or upgrade to modern equivalent. | 500 | 200000 | 218000 | 13
Future Stone Kerbs - Mornington Area | Hargreaves St | Mornington | #N/A | 2019-08-23 | Stone kerbing both sides - For Service Delivery to consider renewal plan i.e. maintain character or upgrade to modern equivalent. | 500 | 200000 | 218000 | 13
Future Stone Kerbs - Mornington Area | Herbert St | Mornington | #N/A | 2019-08-26 | Stone kerbing both sides - For Service Delivery to consider renewal plan i.e. maintain character or upgrade to modern equivalent. | 760 | 304000 | 331360 | 13 | Yes
Future Stone Kerbs - Mornington Area | Grange Rd | Mornington | #N/A | 2019-08-26 | Stone kerbing both sides - For Service Delivery to consider renewal plan i.e. maintain character or upgrade to modern equivalent. | 360 | 144000 | 156960 | 13 | Yes

## Defined List
Priority | Proposed Year | Cost Estimate (Proposed Actual) |  | Cost Estimate (include 9% cont to match Downer)
1 | 2020/21 | Average renewal rate per m | 400 | Downer contingency | 1.09
2 | 2021/22
3 | 2022/23
4 | 2023/24
5 | 2024/25
13 | Stone kerbing